## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
STT | Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration | Start Time | Deadline | Finish Time | Resit | Note
1 | Database | List of book products | Simple | Iteration 1 | SE150430 | Đặng Minh Tuấn | Iteration 1 | 2023-02-12 | 2023-02-15 | 2023-02-15 |  | Finished On Time | Đặng Minh Tuấn | 11 | Đặng Minh Tuấn | SE150430
2 | Database | Database Book Genre | Simple | Iteration 1 | CE160821 | Bùi Trần Vũ Quyên | Iteration 1 | 2023-02-12 | 2023-02-15 | 2023-02-15 |  | Finished On Time | Bùi Trần Vũ Quyên | 12 | Bùi Trần Vũ Quyên | CE160821
3 | Database | Supplier Database | Simple | Iteration 1 | CE160376 | Cao Phúc Khang | Iteration 1 | 2023-02-12 | 2023-02-15 | 2023-02-15 |  | Finished On Time | Nguyễn Thành Đồng | 9 | Nguyễn Thành Đồng | CE160634
4 | User | Login function | Medium | Iteration 1 | CE160821 | Bùi Trần Vũ Quyên | Iteration 1 | 2023-02-12 | 2023-02-15 | 2023-02-15 |  | Finished On Time | Cao Phúc Khang | 10 | Cao Phúc Khang | CE160376
5 | User | Registration function | Complex | Iteration 1 | CE160821 | Bùi Trần Vũ Quyên | Iteration 1 | 2023-02-12 | 2023-02-17 | 2023-02-15 |  | Finished Early |  |  | --- | ---
6 | User | Check login, registration | Complex | Iteration 1 | CE160821 | Bùi Trần Vũ Quyên | Iteration 1 | 2023-02-12 | 2023-02-17 | 2023-02-17 |  | Finished On Time
7 | User | Log out | Simple | Iteration 1 | SE150430 | Bùi Trần Vũ Quyên | Iteration 1 | 2023-02-14 | 2023-02-19 | 2023-02-18 |  | Finished Early
8 | Database | Create a list of admin accounts and customers | Simple | Iteration 1 | CE160634 | Nguyễn Thành Đồng | Iteration 1 | 2023-02-14 | 2023-02-19 | 2023-02-18 |  | Finished Early
9 | User | Book search function | Medium | Iteration 1 | CE160634 | Nguyễn Thành Đồng | Iteration 1 | 2023-02-14 | 2023-02-19 | 2023-02-19 |  | Finished On Time
10 | User | Add, delete, update cart | Complex | Iteration 1 | CE160821 | Bùi Trần Vũ Quyên | Iteration 1 | 2023-02-14 | 2023-02-19 | 2023-02-19 |  | Finished On Time
11 | User | Contact function | Simple | Iteration 1 | CE160376 | Cao Phúc Khang | Iteration 1 | 2023-02-15 | 2023-02-18 | 2023-02-17 |  | Finished Early
12 | User | Menu - Latest products, favorites, highlights, recommendations | Simple | Iteration 1 | SE150430 | Đặng Minh Tuấn | Iteration 1 | 2023-02-15 | 2023-02-18 | 2023-02-18 |  | Finished On Time
13 | User | Book section discount, favorite, featured, rated, recommended, special | Simple | Iteration 1 | SE150430 | Đặng Minh Tuấn | Iteration 1 | 2023-02-15 | 2023-02-18 | 2023-02-18 |  | Finished On Time
14 | User | Personal information interface | Medium | Iteration 1 | CE160634 | Nguyễn Thành Đồng | Iteration 1 | 2023-02-19 | 2023-02-25 | 2023-02-24 |  | Finished Early
15 | User | Edit, delete, update customer information | Complex | Iteration 1 | CE160634 | Nguyễn Thành Đồng | Iteration 1 | 2023-02-19 | 2023-02-25 | 2023-02-25 |  | Finished On Time
16 | User | Change Password | Medium | Iteration 1 | CE160634 | Nguyễn Thành Đồng | Iteration 1 | 2023-02-19 | 2023-02-22 | 2023-02-22 |  | Finished On Time
17 | User | Customer information overview interface | Simple | Iteration 1 | CE160376 | Cao Phúc Khang | Iteration 1 | 2023-02-18 | 2023-02-23 | 2023-02-23 |  | Finished On Time
18 | User | Order interface | Simple | Iteration 1 | CE160376 | Cao Phúc Khang | Iteration 1 | 2023-02-19 | 2023-02-24 | 2023-02-24 |  | Finished On Time
19 | User | Order notification interface | Simple | Iteration 1 | CE160376 | Cao Phúc Khang | Iteration 1 | 2023-02-20 | 2023-02-25 | 2023-02-25 |  | Finished On Time
20 | User | Feedback interface | Simple | Iteration 1 | CE160376 | Cao Phúc Khang | Iteration 1 | 2023-02-23 | 2023-02-28 | 2023-02-27 |  | Finished Early
21 | Admin | Create interface to display user management list | Simple | Iteration 1 | SE150430 | Đặng Minh Tuấn | Iteration 1 | 2023-02-16 | 2023-02-23 | 2023-02-23 |  | Finished On Time
22 | Admin | Search function in User Management | Medium | Iteration 1 | CE160376 | Cao Phúc Khang | Iteration 1 | 2023-02-16 | 2023-02-21 | 2023-02-21 |  | Finished On Time
23 | Admin | Function add administrator | Medium | Iteration 1 | SE150430 | Đặng Minh Tuấn | Iteration 1 | 2023-02-17 | 2023-02-22 | 2023-02-22 |  | Finished On Time
24 | Admin | Account authorization, lock status | Simple | Iteration 1 | SE150430 | Đặng Minh Tuấn | Iteration 1 | 2023-02-18 | 2023-02-20 | 2023-02-20 |  | Finished On Time
25 | Admin | Add, edit, delete customer information updates | Complex | Iteration 1 | SE150430 | Đặng Minh Tuấn | Iteration 1 | 2023-02-21 | 2023-02-25 | 2023-02-25 |  | Finished On Time
26 | Admin | Page number display function | Medium | Iteration 1 | CE160376 | Cao Phúc Khang | Iteration 1 | 2023-02-21 | 2023-02-22 | 2023-02-22 |  | Finished On Time
27 | Admin | The homepage shows the overview interface | Medium | Iteration 1 | CE160821 | Bùi Trần Vũ Quyên | Iteration 1 | 2023-02-23 | 2023-02-27 | 2023-02-26 |  | Finished Early
28 | Admin | Book Management | Complex | Iteration 1 | CE160821 | Bùi Trần Vũ Quyên | Iteration 1 | 2023-02-23 | 2023-03-02 | 2023-03-01 |  | Finished Early
29 | Admin | Product search function, display interface | Medium | Iteration 1 | CE160376 | Cao Phúc Khang | Iteration 1 | 2023-02-26 | 2023-03-02 | 2023-03-01 |  | Finished Early
30 | Admin | book information | Medium | Iteration 1 | CE160821 | Bùi Trần Vũ Quyên | Iteration 1 | 2023-03-01 | 2023-03-05 | 2023-03-05 |  | Finished On Time
31 | Admin | Function to add, edit, delete product information | Medium | Iteration 1 | CE160821 | Bùi Trần Vũ Quyên | Iteration 1 | 2023-02-23 | 2023-02-27 | 2023-02-26 |  | Finished On Time
32 | Admin | Category list | Medium | Iteration 1 | CE160634 | Nguyễn Thành Đồng | Iteration 1 | 2023-02-23 | 2023-03-02 | 2023-03-01 |  | Finished On Time
33 | Admin | Search, add new book genres | Simple | Iteration 1 | CE160376 | Cao Phúc Khang | Iteration 1 | 2023-03-01 | 2023-03-05 | 2023-03-05 |  | Finished On Time
34 | Admin | Function to edit and delete book genre information | Medium | Iteration 1 | CE160634 | Nguyễn Thành Đồng | Iteration 1 | 2023-02-23 | 2023-02-27 | 2023-02-27 |  | Finished On Time
35 | Admin | Warehouse management interface | Simple | Iteration 1 | SE150430 | Đặng Minh Tuấn | Iteration 1 | 2023-02-28 | 2023-03-02 | 2023-03-02 |  | Finished On Time
36 | Admin | Supplier List | Simple | Iteration 1 | CE160634 | Nguyễn Thành Đồng | Iteration 1 | 2023-03-02 | 2023-03-05 | 2023-03-05 |  | Finished On Time
37 | Admin | More suppliers | Medium | Iteration 1 | CE160634 | Nguyễn Thành Đồng | Iteration 1 | 2023-03-02 | 2023-03-05 | 2023-03-05 |  | Finished On Time
38 | Admin | Help management function | Medium | Iteration 1 | CE160821 | Bùi Trần Vũ Quyên | Iteration 1 | 2023-02-28 | 2023-03-05 | 2023-03-05 |  | Finished On Time
39 | Admin | Show contact information | Simple | Iteration 1 | CE160821 | Bùi Trần Vũ Quyên | Iteration 1 | 2023-02-28 | 2023-03-05 | 2023-03-05 |  | Finished On Time
40 | Admin | Order management function | Complex | Iteration 1 | SE150430 | Đặng Minh Tuấn | Iteration 1 | 2023-03-03 | 2023-03-10 | 2023-03-10 |  | Finished On Time
41 | Admin | New menu list | Complex | Iteration 1 | SE150430 | Đặng Minh Tuấn | Iteration 1 | 2023-02-28 | 2023-03-02 | 2023-03-02 |  | Finished On Time
42 | Admin | Packing list | Complex | Iteration 1 | SE150430 | Đặng Minh Tuấn | Iteration 1 | 2023-03-03 | 2023-03-10 | 2023-03-10 |  | Finished On Time